## Sheet1
Project | Date | Part | Phase | Start Time | Int. Time | Stop Time (min) | Cumulative | Delta time (min) | Comments
MLA | 2015-05-07 | Testing | Coding(Testing drag drop functionality) | 900 | 10 | 1020 | 70 | 70 | Return true if img1 = div1
|  | Testing | Planning | 1020 | 0 | 1055 | 35 | 105 | Coding standards, rough Class diagram
|  | Testing | Coding | 1110 | 10 | 1240 | 80 | 185 | Hangman
| 2015-05-11 | Testing | Coding | 910 | 10 | 1010 | 50 | 235 | Added letters to lower (shouldn't matter for app), added checker to see if letter has been guessed
| 2015-05-12 | Testing | Coding | 930 | 5 | 1000 | 25 | 260 | Fixed the MVC functionality
| 2015-05-17 | Testing | Planning | 1400 | 30 | 1630 | 120 | 380 | Use case and functionality list for basic drag and drop
| 2015-05-18 | Testing | Coding | 900 | 0 | 1000 | 60 | 440 | Testing file loader, need a server
|  | Iteration One | Coding | 1100 | 10 | 1140 | 30 | 470 | Scrapped Jquery for file loading, reverted to basic fileHandler
| 2015-05-21 | Iteration One | Coding | 815 | 0 | 1000 | 105 | 575
| 2015-05-26 | Iteration One | Coding | 840 |  | 950 | 70 | 645 | Fixed buttons reloading page (default use is for form), removed MVC for iteration one
|  | Iteration One | Coding | 1000 | 30 | 1200 | 90 | 735 | Successful implementation of one question
|  | Iteration Two | Coding | 1600 | 90 | 2020 | 150 | 885 | First iteration complete
| 2015-06-02 | Iteration Two | Coding | 830 | 0 | 930 | 60 | 945 | Coded timer in javascript
|  | Iteration Two | Coding | 1000 | 20 | 1200 | 100 | 1045 | Started iteration 2, transferred all to classes, implemented stopwatch
|  | Iteration Three | Coding | 1330 | 60 | 1830 | 300 | 1345 | Started Iteration 3, implemented MVC functionality, implemented User class, implemented history of questions, implemented titles of questions, can sort by title, JS Linted all javascript
| 2015-06-03 | Iteration Three | Coding | 1030 | 0 | 1100 | 30 | 1375 | Created results pop-up window
| 2015-06-04 | Iteration Three | Coding | 830 | 0 | 1000 | 90 | 1465 | Implemented ability to retry the same quiz, workaround to clear innerHTML, possible memory leak? Issue: history of questions was cutting the last question off, fixed by moving getNextQuestion() (inside the onClick function) below the createHistory() function
| 2015-06-05 | Iteration Three | Coding | 1630 | 40 | 1830 | 80 | 1545 | Forgot that javascript had a built in sorting function.
|  | Iteration Three | Coding | 1930 | 40 | 2100 | 50 | 1595 | Implemented different results - 1 by chronological order, 1 sorted by correct results (&time)
| 2015-06-09 | Iteration Three | Coding | 830 | 15 | 950 | 65 | 1660 | Implemented local storage for results
|  | Iteration Three | Coding | 1000 | 40 | 1200 | 80 | 1740 | Fixed bug - time storage in ms wasn't being converted to MM:ss:mmm correctly - if miliseconds was less than 100, was not translated to a string correctly; implemented local storage retrieval for results; began work on username field
| 2015-06-12 | Iteration Four | Coding | 1600 | 120 | 2200 | 240 | 1980 | created splash screen, implemented drag and drop, canvas and animation elements
| 2015-06-13 | Iteration Four | Coding | 1600 | 120 | midnight | 360 | 2340 | Implemented sound on both splash screen and app, began conversion to chromeapp, BUG - local storage (not declaring in manifest, still not working)
| 2015-06-14 | Iteration Four | Testing | 1500 | 120 | midnight | 420 | 2760 | Jasmine
| 2015-06-15 | Iteration Four | Documentation | [5 empty] | design diagrams,
| 2015-06-16 | Iteration Four | Documentation